## 1
Tentative Project time Line Schedule
| Project Name | [23 empty] | project duration Time | [10 empty] | Note
| KFUPM Smart Gates Project | [23 empty] | SART |  |  |  | 25-12-2020 | [6 empty] | Actual Time | [5 empty] | 6 Months
[25 empty] | FINISH |  |  |  | 25-06-2021 | [6 empty] | Requested Time | [5 empty] | 9 Months
NO | Description of works | DATE |  | 2020 | [5 empty] | 2021
|  | Start | Finish | DEC | [5 empty] | JAN | [5 empty] | FEB | [5 empty] | MAR | [5 empty] | APR | [5 empty] | MAY | [5 empty] | JUN
|  |  |  | 5 | 10 | 15 | 20 | 25 | 31 | 5 | 10 | 15 | 20 | 25 | 31 | 5 | 10 | 15 | 20 | 25 | 29 | 5 | 10 | 15 | 20 | 25 | 31 | 5 | 10 | 15 | 20 | 25 | 30 | 5 | 10 | 15 | 20 | 25 | 31 | 5 | 10 | 15 | 20 | 25 | 30
* | Arranging the necessary Required documents | 25/12/2020 | 31/12/2020 | bar: DEC 25 to DEC 31
* | Orders Local Materials and Main Equipments System out | 25/12/2020 | 31/12/2020 | bar: DEC 25 to DEC 31
A | The 1st Stage
Digging, Drilling, Civil construction Works
1 | Determind & mark All PointsLocations for all devices in all Gates. | 31/12/2020 | 2021-10-01 | bar: DEC 31 to JAN 10
2 | Arrange & Deliver materials for civil works required for | 2021-05-01 | 15/01/2021 | bar: JAN 5 to JAN 15
3 | Removal of asphalt and concrete works and re-implementation | 2021-10-01 | 2021-10-02 | bar: JAN 10 to FEB 10
4 | Remove Build & Supply Guard Room in Gate (2) with wall Necessary | 2021-10-01 | 20/02/2021 | bar: JAN 10 to FEB 20
5 | Doing Infrastructure works all Gates to Building NO.21 | 20/01/2021 | 25/03/2021 | bar: JAN 20 to MAR 25
6 | creation of new manholes to the Head-end | 2021-10-02 | 25/02/2021 | bar: FEB 10 to FEB 25
7 | Duct Bank Work | 15/02/2021 | 2021-10-03 | bar: FEB 15 to MAR 10
8 | Installation all Concrete Foundations for Mounting Poles | 25/02/2021 | 2021-10-03 | bar: FEB 25 to MAR 10
9 | Installation Infrastructure pipes for Main Powers & Networks | 15/02/2021 | 2021-10-03 | bar: FEB 15 to MAR 10
10 | Completion of the asphalt works, concrete and interlock installation | 15/03/2021 | 2021-05-04 | bar: MAR 15 to APR 5
11 | Civil & Constructions Finishing | 15/03/2021 | 20/03/2021 | bar: MAR 15 to MAR 20
B | The 2nd Stage
Powers, Cable Networks & Fieled Equipments
1 | Installation of Steel Weather Proof Cabinets & Junction Boxes | 2021-05-02 | 25/02/2021 | bar: FEB 5 to FEB 25
2 | Installation of External Pedestals for Fiber & Data network distrbutions and fiber Holder. | 15/02/2021 | 25/02/2021 | bar: FEB 15 to FEB 25
3 | Fixing All Mounting Poles in Foundations | 15/03/2021 | 25/03/2021 | bar: MAR 15 to MAR 25
4 | Installation Elect Main Power Panel Boxes Including accessorice. | 25/02/2021 | 2021-10-03 | bar: FEB 25 to MAR 10
5 | Installation Elect Sub Power Panel Boxes Including accessorice. | 29/02/2021 | 15/03/2021 | bar: FEB 29 to MAR 15
6 | Transferring of existing power supply from existing Location | 2021-05-03 | 2021-10-03 | bar: MAR 5 to MAR 10
7 | Installing New Electric Sokets & Adapters As per Standard | 20/03/2021 | 31/03/2021 | bar: MAR 20 to MAR 31
8 | Installing PVC EMT Nema Under Ground Duct Bank Work | 20/03/2021 | 31/03/2021 | bar: MAR 20 to MAR 31
9 | Installation of GI External Pipes for Outdoor Devices with finishing | 15/04/2021 | 25/04/2021 | bar: APR 15 to APR 25
10 | Install & Pulling New Fiber, Data, and power Cabels trough all the new & Existing Conduits | 2021-05-04 | 15/05/2021 | bar: APR 5 to MAY 15
11 | Splicing, Jointing, Crimping to be ready for all devices System | 25/04/2021 | 15/05/2021 | bar: APR 25 to MAY 15
12 | Installation Industrial Convertors & Switches and accessories in Steel Boxes. | 20/04/2021 | 2021-05-05 | bar: APR 20 to MAY 5
13 | Installation of all Mounting Poles and necessary Brackets | 15/03/2021 | 30/04/2021 | bar: MAR 15 to APR 30
14 | Test All Networks & Powers Cabels | 2021-05-05 | 2021-10-05 | bar: MAY 5 to MAY 10
C | The 3rd Stage
Installation Main Devices Systems
1 | Deiver All main Devices Systems to KFUPM Store. | 29/02/2021 | 2021-10-05 | bar: FEB 29 to MAR 10
2 | Installation RFID UHF Readers with Termination & Cabling | 29/02/2021 | 31/03/2021 | bar: FEB 29 to MAR 31
3 | Installation ANPR with Termination & Cabling | 29/02/2021 | 2021-05-04 | bar: FEB 29 to APR 5
4 | Installation Gate Barriers with Adjusting, Termination & Cabling | 2021-10-03 | 15/04/2021 | bar: MAR 10 to APR 15
5 | Installation Signals Light to the mounting with Adjusting, Termination & Cabling | 25/03/2021 | 15/04/2021 | bar: MAR 25 to APR 15
6 | Installation CCTV Survellance with Adjusting, Termination & Cabling | 2021-10-04 | 20/04/2021 | bar: APR 10 to APR 20
7 | Installation Industrial Convertors & Switches in Cabinets with Termination & Cabling | 15/03/2021 | 31/03/2021 | bar: MAR 15 to MAR 31
8 | Installation the Kiosk Cladding with Concete Foundations | 20/03/2021 | 31/03/2021 | bar: MAR 20 to MAR 31
9 | Installation Panic Alarm Gates 1,2,3 & 4 Adjusting, Termination & Cabling | 15/04/2021 | 2021-05-05 | bar: APR 15 to MAY 5
10 | Installation Intercom in Kiosk Adjusting, Termination & Cabling Gate.1 | 31/03/2021 | 2021-05-04 | bar: MAR 31 to APR 5
11 | Installation LED Signage Frame, Mold, Stand | 2021-10-04 | 20/04/2021 | bar: APR 10 to APR 20
12 | Installation Digital Signage inside the mold & termination, Cabling | 15/04/2021 | 20/04/2021 | bar: APR 15 to APR 20
13 | Connectin All devices to the Main & Sub Elect Power Panels | 15/04/2021 | 25/04/2021 | bar: APR 15 to APR 25
14 | Connecting All devices To the Main Industrial Data Switches | 15/04/2021 | 25/04/2021 | bar: APR 15 to APR 25
15 | Installation Traffic Mirrors | 30/04/2021 | 2021-05-05 | bar: APR 30 to MAY 5
D | The 4th Stage
Control Room & Management Work Stations (Belg.21)
1 | Installation The Management Server | 25/03/2021 | 31/03/2021 | bar: MAR 25 to MAR 31
2 | Installations the Workstations and Rack mount | 31/03/2021 | 2021-05-04 | bar: MAR 31 to APR 5
3 | Connecting the systems to main Core switches & SFP | 31/03/2021 | 2021-05-04 | bar: MAR 31 to APR 5
4 | Configuration All IP Data Networks | 2021-10-04 | 20/04/2021 | bar: APR 10 to APR 20
5 | Installations & Configuration the License and Software RFID and ANPR | 2021-10-04 | 2021-10-05 | bar: APR 10 to MAY 10
6 | Installations License & Configuration Panic Sys, | 2021-10-05 | 15/05/2021 | bar: MAY 10 to MAY 15
7 | Installation the License Milestone Updated in Existing Sys. | 2021-05-05 | 15/05/2021 | bar: MAY 5 to MAY 15
8 | Installations License & Configuration LED Signage | 15/05/2021 | 20/05/2021 | bar: MAY 15 to MAY 20
9 | Installations License & Configuration Intercom Device | 20/05/2021 | 25/05/2021 | bar: MAY 20 to MAY 25
10 | Level & Adjustments RFID, ANPR & CCTV | 25/05/2021 | 31/05/2021 | bar: MAY 25 to MAY 31
E | FINAL Stage
Testing, Integrate, Training & Documentations
1 | Testing and Commissioning | 25/05/2021 | 2021-10-06 | bar: MAY 25 to JUN 10
2 | Labling | 20/05/2021 | 31/06/2021 | bar: MAY 20 to MAY 31
3 | Data Backup from Mawaqif Old System | 31/05/2021 | 15/06/2021 | bar: MAY 31 to JUN 15
4 | Programing & Integrate the Existing SQL KFUPM data base with new System. | 25/05/2021 | 25/25/2021 | bar: MAY 25 to JUN 25
5 | Training | 15/06/2021 | 25/06/2021 | bar: JUN 15 to JUN 25
6 | Documentations, Project Manual Operating | 2021-10-06 | 25/06/2021 | bar: JUN 10 to JUN 25
7 | Drawing | 2021-05-06 | 25/06/2021 | bar: JUN 5 to JUN 25
8 | Remove the old Existing System (Mawqif) | 20/06/2021 | 25/06/2021 | bar: JUN 20 to JUN 25
[5 empty] | Planning | [6 empty] | Stages

## Sheet1
PROJECT SCHEDULE
Starting
A. Checking of all Existing Line amplifiers(the one to be replaced). |  |  | 24/7/2011
B. 1st Partial Delivery |  |  |  | 2011-06-08
C. Basic Assembly and installation of the Rack, COFDM Modules, |  |  |  |  | 7/8/11 - 9/8/11
Power supply, combiners etc…
D. Checking of Satellite signals (Newly proposed Location) | [5 empty] | 2011-11-08
E. Arranging the Civil and related works to install the Line amplifiers
in your Supplied Pedestals. | [6 empty] | 27/8/2011 | 18/9/2011
F. Foundation for the dishes, Excavation and laying of conduits to the
Head-end Room | [7 empty] | 2011-03-09 | 2011-06-09
G. Installation of Dish Antennas, LNBS | [8 empty] | 2011-06-09 | 2011-08-09
2nd Partial Delivery | [8 empty] | 2011-06-09
H. Installation,Configuration, termination of New Head-end |  |  |  |  | 2011-10-09 | 2011-12-09
I. Replacing, Shifiting, Installing, connecting New Line Amplifiers into
the Pedestals. | & | Checking the network and new amps. |  |  |  | 2011-12-09 | 22/9/2011
J. Installation of new cables from the nearest manhole to the head-end | [7 empty] | 24/9/2011
L. Transferring of existing power supply from existing Location to the | [7 empty] | 25/9/2011-26/9/2011
New Head-end Location.
Final Partial Delivery | [7 empty] | 25/9/2011
M. Level Adjustments of All amplifiers | [8 empty] | 25/9/2011 | 27/9/2011
N. Termination, testing and commissioning | [9 empty] | 27/9/2011 ONWARDS | 2011-02-10