## 1
KFUPM - NEW CATV HEAD - END SYSTEM
PROJECT SCHEDULE
Sl. | Description of works | 2011-07-01 |  |  |  |  | 2011-08-01 | [7 empty] | 2011-09-01 | [30 empty] | 2011-10-01
No |  | 24 | 25 | 26 | 27 | 28 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
A | Checking of all Existing | bar: 2011-07-01 24 to 2011-07-01 28
Line amplifiers(the one to be replaced)
B | 1st Partial Delivery | bar: 2011-08-01 6
C | Basic Assembly and installation of the Rack, | bar: 2011-08-01 7 to 2011-08-01 10
COFDM Modules,Power supply, combiners etc…
D | Checking of Satellite signals (Newly proposed Location) | bar: 2011-08-01 10 to 2011-08-01 11
E | Arranging materials for civil works required for | bar: 2011-08-01 31 to 2011-09-01 1
foundations,Pedestals etc.
F | Starting the Civil and related works to install the | bar: 2011-09-01 3 to 2011-09-01 19
Line amplifiers in your Supplied Pedestals.
G | Foundation for the dishes, Excavation and laying | bar: 2011-09-01 3 to 2011-09-01 6
of conduits to the Head-end Room
H | Installation of Dish Antennas, LNBS | bar: 2011-09-01 6 to 2011-09-01 8
2nd Partial Delivery | bar: 2011-09-01 9
I | Installation,Configuration, termination of New Head-end | bar: 2011-09-01 10 to 2011-09-01 12
J | Replacing, Shifiting, Installing, connecting New Line Amplifiers | bar: 2011-09-01 12 to 2011-09-01 22
into the Pedestals & Checking the cable network and new amplifiers
K | Installation of New cables from the nearest | bar: 2011-09-01 24
manhole to the Head-end
L | Transferring of existing power supply from existing Location | bar: 2011-09-01 25 to 2011-09-01 26
to the New Head-end Location
Final Partial Delivery | bar: 2011-09-01 25
M | Level Adjustments of All amplifiers | bar: 2011-09-01 25 to 2011-09-01 28
N | Testing and Commissioning | bar: 2011-09-01 27 to 2011-10-01 2
Planning

## Sheet1
PROJECT SCHEDULE
Starting
A. Checking of all Existing Line amplifiers(the one to be replaced). |  |  | 24/7/2011
B. 1st Partial Delivery |  |  |  | 2011-06-08
C. Basic Assembly and installation of the Rack, COFDM Modules, |  |  |  |  | 7/8/11 - 9/8/11
Power supply, combiners etc…
D. Checking of Satellite signals (Newly proposed Location) | [5 empty] | 2011-11-08
E. Arranging the Civil and related works to install the Line amplifiers
in your Supplied Pedestals. | [6 empty] | 27/8/2011 | 18/9/2011
F. Foundation for the dishes, Excavation and laying of conduits to the
Head-end Room | [7 empty] | 2011-03-09 | 2011-06-09
G. Installation of Dish Antennas, LNBS | [8 empty] | 2011-06-09 | 2011-08-09
2nd Partial Delivery | [8 empty] | 2011-06-09
H. Installation,Configuration, termination of New Head-end |  |  |  |  | 2011-10-09 | 2011-12-09
I. Replacing, Shifiting, Installing, connecting New Line Amplifiers into
the Pedestals. | & | Checking the network and new amps. |  |  |  | 2011-12-09 | 22/9/2011
J. Installation of new cables from the nearest manhole to the head-end | [7 empty] | 24/9/2011
L. Transferring of existing power supply from existing Location to the | [7 empty] | 25/9/2011-26/9/2011
New Head-end Location.
Final Partial Delivery | [7 empty] | 25/9/2011
M. Level Adjustments of All amplifiers | [8 empty] | 25/9/2011 | 27/9/2011
N. Termination, testing and commissioning | [9 empty] | 27/9/2011 ONWARDS | 2011-02-10